Construction of Godowns under Progress:

| Sl. No | Name of the District | MLS point | Capacity in Mts | Progress of work (As on last Board Meeting) | Progress of work (As on Date) |
| --- | --- | --- | --- | --- | --- |
| 1 | Visakhapatnam | Marripalem G. No. 4 | 500 | Work cancelled, Tenders finalized & Agreement to be concluded. | Brick work upto Air Inlets Top level |
| 2 | West Godavari | Undi G.No.11 | 500 | Brick work completed up to roof level. Trusses fabrication is in progress. | Erection of Trusses completed.AC Sheets roofing work in progress. |
| 3 | West Godavari | Undi G.No.12 | 500 | Brick work completed up to roof level. Trusses fabrication is in progress. | Erection of Trusses completed.AC Sheets roofing work in progress. |
| 4 | Krishna | Mutyallampadu G.No: 2. | 500 | Trusses erection & AC Sheet Roofing is in progress. | Flooring completed. Painting work in progress. |
| 5 | Krishna | Mutyallampadu G No.3 | 500 | Brick work completed up to Roof level. | Roofing completed. Plastering work is in progress |
| 6 | Krishna | Mutyallampadu G. No.4 | 500 | Brick work completed up to Roof level. | Roofing completed. Plastering work is in progress |
| 7 | Mahabubnagar | Kalwakurthy | 600 | Brick work completed up to Roof level. | Brick work completed up to Roof level. |
| 8 | Mahabubnagar | Nagarkurnool | 600 | Brick work completed up to Roof level. | Work Cancelled. |
| 9 | Mahabubnagar | Nayaranapet | 600 | Completed below basement level. | Completed below basement level. |
| 10 | Mahabubnagar | Amanagal | 600 | Brick work completed up to Roof level. | Brick work completed up to Roof level. |
| 11 | Warangal | Narsampeta G No.2 | 500 | Brick work completed up to roof level. | Work Cancelled. |
| 12 | Warangal | Wardhannapeta G No.2 | 500 | Basement completed | Brick work upto 4.00 m i.e., above tie beam level completed |
| 13 | Warangal | Mahabubabad G No.2 | 500 | Basement completed | Work cancelled. Tenders to be invited. |
| 14 | Warangal | Mahabubabad G No.3 | 500 | Basement completed | Work cancelled. Tenders to be invited. |
| 15 | Ranga Reddy | Hafeezpet G.No.16 | 600 | Sheeting completed and plastering works in progress. | Roofing work completed and plastering works in progress. |
| 16 | Ranga Reddy | Hafeezpet G.No.17 | 600 | Sheeting completed and plastering works in progress. | Roofing work completed and plastering works in progress. |
| 17 | Ranga Reddy | Kismatpura G.No.5 | 600 | Brick work completed up to roof level | Brick work completed up to roof level |
| 18 | Ranga Reddy | Kismatpura G.No.6 | 600 | Brick work completed up to roof level | Brick work completed up to roof level |
| 19 | Ranga Reddy | Kismatpura G.No.7 | 600 | Brick work completed up to roof level | Brick work completed up to roof level |
| 20 | Ranga Reddy | Kismatpura G.No.8 | 600 | Brick work completed up to roof level | Brick work completed up to roof level |
| 21 | Ranga Reddy | Kismatpura G.No.9 | 600 | Brick work completed up to roof level | Brick work completed up to roof level |
| 22 | Ranga Reddy | Kismatpura G.No.10 | 600 | Brick work completed up to roof level | Brick work completed up to roof level |
| 23 | Nalgonda | Nalgonda G.No:2 | 500 | Plinth beam level. | Work cancelled. |
| 24 | Nalgonda | Nalgonda G.No: 3 | 500 | Plinth beam level. | Plinth beam level. |
| 25 | Nalgonda | Tungaturthi | 600 | Trusses errection & AC Sheets Roofing completed & Plastering in progress. | Flooring work is under progress |
| 26 | Medak | Narayankhed G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Work could not be started due to site dispute |
| 27 | Medak | Narayankhed G.No: 2 | 500 | Tenders finalized. Agreement to be concluded. | Work could not be started due to site dispute |
| 28 | Karimnagar | Korutla, G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Footings completed. RR work is under progress. Work stopped for last 2 month due to Court Case. |
| 29 | Karimnagar | Korutla, G.No: 2 | 500 | Agreement concluded & Marking to be given. | Footings completed. RR work is under progress. Work stopped for last 2 month due to Court Case. |
| 30 | Karimnagar | Manthani, G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Site dispute |
| 31 | Karimnagar | Manthani, G. No: 2 | 500 | Tenders finalized. Agreement to be concluded. | Site dispute |
| 32 | Karimnagar | Choppadandi, G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Site dispute |
| 33 | Karimnagar | Choppadandi, G.No: 2 | 500 | Tenders finalized. Agreement to be concluded. | Site dispute |
| 34 | Karimnagar | Jammikunta, G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Work could not be started due to Court Case |
| 35 | Karimnagar | Jammikunta, G.No: 2 | 500 | Tenders finalized. Agreement to be concluded. | Work could not be started due to Court Case |
| 36 | Karimnagar | Vemulawada, G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Work completed upto basement level |
| 37 | Karimnagar | Vemulawada, G.No: 2 | 500 | Tenders finalized. Agreement to be concluded. | Work completed upto basement level |
| 38 | Karimnagar | Sircilla, G.No: 1 | 500 | Tenders finalized. Agreement to be concluded. | Work completed upto basement level. Columns work above plinth beam level and brick work in progress. |
| 39 | Karimnagar | Sircilla, G.No: 2 | 500 | Tenders finalized. Agreement to be concluded. | Work completed upto basement level. Columns work above plinth beam level and brick work in progress. |
|  |  | Total | 20,800 Mts |  |  |